## Sheet 1
Project Financial Estimates May 2023
| Outgoings | Income
Payments Made to Date | 22414.38
Estimated outstanding project cost | 335553.03
(See Sheet 2)
S106 |  | 255563.85
NTC |  | 18500
Rugby Club Loan |  | 40000
Rugby Club Donation |  | 20000
Anonymous donation |  | 3000
Anonymous donation |  | 300
Steve Gooch Donation |  | 1000
Total Estimated Outgoings | 357967.41
Current Total Project Income |  | 338363.85
Surplus/Shortfall |  |  | -19603.56

## Sheet 2
Newent Community Hall - Budget Estimate April 2023
Item Ref | Description | Cost £
1 | Contract Sum Evergreen Developments | 316230.73
2 | Provisional Allowance for VAT on contract sum pending clarification of VAT exemption | 63246.14
3 | Fees for discharge of planning conditions. (Estimated) Including VAT | 540
4 | JCT Contract Form Fee Cost (Including VAT) | 96
5 | Remaining calfordseaden professional fees for administration of contract to completion incuding VAT (Excluding costs for future disbursements for travelling expenses) | 11520
6 | Estimated costs for remaining expenses for site visits including VAT. | 700
7 | Remaining Costs for Principal Designer role including VAT. | 1554
8 | Provisional sum for environmental issues in respect of trees and hedges. (Ecology advice) as well as costs for provision of trees and planting. | 1750
9 | Project contingency (excluding VAT) as discussed with Roger Beard. | 15811.54
10 | Provisional Allowance for VAT on project contingency pending clarification of VAT exemption | 3162.3
| Sub Total | 414610.71
| Potential saving on VAT on building works and contingency pending formal confirmation of VAT exemption. | 79057.68
| Total Budget (VAT status depending) | 335553.03